## Cover
MoH D6 & D7 Proactive Validator Checklist
Working instrument for the ITU Project Manager — extended beyond the original 50-item participant checklist
Programme | Progressa Enterprise Architecture Programme — [contract reference]
Audience | ITU Project Manager (validator), ITU Analyst (scribe), MoH Review Coordinator
Purpose | Force active verification of each validation statement — probes, evidence, red flags — instead of passive ‘confirm’
Companion | MoH D6 & D7 Validation Checklist.pdf (50 items); MoH_D6_D7_Validation_Session.pptx (23 slides); 3-Day Agenda v1.1 (PM-led)
Version | v1.0 — 19 April 2026
How to use this workbook
1. | Work through tabs in order. V0 before Day 1; P on Day 1 morning; B/D/A/I/T/R1/R2/R3/R4 during sessions; G/L in parallel with Day 1–3; K in Day 3 morning; X between sessions; S and PR at session close-outs.
2. | For each core item: read the Statement to the room; ask BOTH probes; wait for substantive answers; record Evidence. Only mark Confirmed OK if evidence is present AND no red-flag pattern was uttered.
3. | If a Red-flag pattern is heard, do NOT mark Confirmed. Classify instead as Clarification / Correction / Objection / Enhancement per the rules.
4. | Any deep-technical question beyond the PM brief is PARKED verbatim and deferred to the Lead Architect for written response within 48 hours of Day 3 close.
5. | Linked items: if you classify an item, check every item listed in Linked — there is likely a propagation effect.
6. | At end of each day: run Tab 16 (Process Integrity) self-check before leaving the room. At end of Day 3: Tab 17 (Dashboard) must show zero Pending before the decision memo is signed.
Classification legend
Category | Meaning | Priority
Confirmed OK | Statement is accepted with evidence; no red-flag pattern. | NONE
Correction | A factual error that must be fixed. | HIGH
Clarification | Unclear or insufficiently evidenced; needs more info before Confirm. | MEDIUM
Enhancement | A suggestion to improve; not blocking. | LOW
Objection | Fundamental disagreement; cannot proceed without resolution. | CRITICAL
N/A | Item does not apply to this workshop / stakeholder. | NONE
Pending | Not yet reviewed. | NONE

## V0 Pre-workshop
V0 — Pre-workshop Readiness (run BEFORE Day 1)
ID | Check / Statement | How to Verify (Procedure / Probe) | Evidence Required | Red-flag Pattern | Owner | Status | Notes
V01 | Participant list is complete; every mandatory attendee has accepted. | Review RSVP tracker; for each mandatory role cross-check acceptance. | Signed attendance commitment per mandatory role. | Any unreturned mandatory RSVP → escalate to PS chief of staff. | ITU Analyst | Pending
V02 | All participants received digital pack (D6, D7, checklist) by T-10. | Send tracker; re-send to non-openers. | E-mail receipts; read-receipt log (where available). | ≥30% of participants didn’t open by T-5 → PM calls them directly. | ITU Analyst | Pending
V03 | Printed bundles delivered to each attendee by T-5. | Physical stock count; delivery confirmation. | Courier / MoH logistics sign-off. | Less than one bundle per seat → Blocked. | MoH logistics | Pending
V04 | PS delegation pre-read briefing completed (T-7). | Calendar shows 60-min slot; briefing pack delivered. | Briefing deck; PS office confirmation. | PS delegation didn’t attend → reschedule pre-read. | ITU Project Manager | Pending
V05 | Each programme lead walk-through completed (T-3). | 8 walk-throughs done; notes captured. | Walk-through notes per programme lead. | Missed walk-through → cover with live briefing Day 1 morning. | ITU Project Manager | Pending
V06 | Decision signatories (PS, PDGA DG, RDIP PM) confirmed attendance for entire Day 3. | Calendar holds in all three diaries. | Dual-confirmed calendar invitations. | Any partial attendance → decision-memo plan B. | PS Chief of Staff | Pending
V07 | Venue booked, tested (projector, network, breakout). | Walk the room T-1; test projector; test network speed. | Test report; contingency laptop + HDMI adapter. | Network < 10 Mbps → print-only fallback prepared. | ITU Analyst + MoH logistics | Pending
V08 | Feedback log spreadsheet prepared and tested; real-time editing works. | Dry-run populate 3 test items. | Test-populated feedback log. | Cloud-sync flaky → use local + manual sync. | ITU Analyst | Pending
V09 | Parking-lot flipchart and coloured-dot stickers available. | Physical inventory in the room. | Photo of set-up. | Missing → procure day-before. | ITU Analyst | Pending
V10 | Category posters (CORRECTION / CLARIFICATION / ENHANCEMENT / OBJECTION) printed and mounted. | Wall-mount in sight of every participant. | Photo of posters. | Missing → print on A3. | ITU Analyst | Pending
V11 | PM T-8 hand-over from Lead Architect complete; hotspot list in hand. | Half-day session completed; PM briefing pack received. | Hand-over meeting notes; hotspot list. | Any slide the PM cannot explain in their own words → extra coaching. | ITU PM + Lead Architect | Pending
V12 | PM has scripted responses for the top-5 likely objections. | Review objection playbook; PM rehearsal. | Scripted responses document. | PM hasn’t rehearsed → last-day rehearsal mandatory. | ITU Project Manager | Pending
V13 | Attendance register and badges prepared. | Printed register + pre-printed badges. | Sign-in table ready. | Missing → improvise Day 1 morning. | ITU Analyst | Pending
V14 | Catering confirmed for all 3 days (coffee breaks, lunches). | Confirmed with caterer; dietary requests collected. | Catering confirmation. | Not confirmed → PM follow-up. | MoH logistics | Pending
V15 | Emergency technical contact (Lead Architect) reachable within 48h. | Architect’s phone/e-mail distributed to PM team. | Contact sheet. | Unreachable — backup contact named. | ITU Project Manager | Pending

## P Premise
P — D5 Premise Re-confirmation (Day 1 morning, S1.2)
ID | Check / Statement | How to Verify (Procedure / Probe) | Evidence Required | Red-flag Pattern | Owner | Status | Notes
P01 | ~90 health facilities figure accepted by MoH delegation. | Facilitator reads figure; pause for objection. | No floor objection. | Any objection → Correction; escalate to D5 re-open decision. | Director of Health Services | Pending
P02 | 2–3M population served figure accepted. | Facilitator reads; pause for objection. | No objection. | Objection on population → Correction. | MoH PS | Pending
P03 | Eight digital systems list is complete (no missing system). | Read list: DHIS2, eCRVS/CIVIS, e-NHIS, SPT, A-LIS, OpenLMIS pilot, SMS for Health, Stock-out module(?). | Programme leads confirm no omission. | Any programme lead names a missing system → Correction. | DHDD Director + programme leads | Pending
P04 | The single automated integration (SPT-to-DHIS2) is accurate. | Facilitator reads; ask if any other automation exists. | No missing automation. | Someone names another automation → Correction to D5 and cascades. | HMIS Coordinator | Pending
P05 | ~90% paper-clinical-records figure accepted. | Read figure; pause. | No objection. | Objection → Clarification. | Director of Health Services | Pending
P06 | ~50% eCRVS population coverage accepted. | Read figure; eCRVS lead confirms. | eCRVS confirmation. | eCRVS lead disputes → Correction. | eCRVS/CIVIS lead | Pending
P07 | ~30% e-NHIS enrolment (vs 60k target) accepted. | Read figure; NHIA confirms. | NHIA confirmation. | NHIA disputes → Correction. | e-NHIS CEO | Pending
P08 | ~60% national electricity access accepted as baseline for offline-first design. | Read; accept as baseline. | No objection. | Any dispute → Clarification; offline-first principle unchanged. | PDGA DG | Pending

## B Business
Core Validation — Business Architecture (D6 §3)
ID | D6/D7 Ref | Statement | Probe 1 | Probe 2 | Evidence Required | Red-flag Answers | Primary Response Owner | Linked Items | Classification | Verbatim Comment | Proposed Change | Action Owner | Deadline
B01 | D6 §3.1.1 | The three-tier governance structure (NDHSC → DHDD → 3 TWGs) is appropriate for MoH and addresses the current coordination gap across digital health systems. | Who chairs NDHSC, and has the Permanent Secretary explicitly confirmed the chair role? | By which quarter can the Ministerial Order establishing NDHSC realistically be signed? | PS verbal confirmation on record; target quarter for Ministerial Order; Financial Regulations reference for the authority threshold. | “We'd need cabinet consultation” / “Threshold should change” / PS silent → do NOT mark Confirmed. | MoH Permanent Secretary | G04, L02, R102 | Pending
B02 | D6 §3.1.1 | NDHSC composition (14 members, PS chair, quarterly meetings, authority over investments > USD 50,000) is correct and workable. | Do all 14 roles currently exist and have incumbents, or are any vacant / under reorganisation? | Is the quarterly cadence compatible with the PS calendar, and should observer seats exist for PDGA / RDIP / WHO? | Role list with incumbent names; calendar pre-commitment; observer-seat decision. | Role doesn’t exist / cadence rejected / threshold disputed. | MoH Permanent Secretary + DHDD Director | B01 | Pending
B03 | D6 §3.1.2 | Upgrading the HMIS team to the Digital Health and Data Directorate (DHDD), with 14 positions across 6 functional areas phased 2025–2028, is realistic within MoH administrative constraints. | Under which civil-service grades do the 14 positions fall, and does the PSC recruitment calendar allow the phased schedule? | Are the proposed salaries competitive against the Progressa ICT market, and what secondment or RDIP top-up is planned if not? | Civil-service grading letter; PSC recruitment calendar commitment; salary benchmark; RDIP supplementation plan. | “The grades don’t exist” / “The salaries are uncompetitive” → Correction. | MoH PS + DHDD Director + PSC liaison | K04, G09 | Pending
B04 | D6 §3.2 | The capability maturity targets (Level 3–4 by 2033 for core health-information capabilities) are ambitious but achievable given the investment and timeframes proposed. | Against which maturity-model definition are the levels measured (HIMSS / OpenHIE / custom)? | If Wave 1 delivery slips by 6 months, which targets most at risk and does the roadmap admit that? | Named maturity-model reference; sensitivity analysis in roadmap. | “We need to see the maturity rubric” → Clarification. | DHDD Director | R105 | Pending
B05 | D6 §3.3 | The eight priority business processes selected for digitisation correctly reflect MoH’s priorities. | Is there a process missing from the list (e.g. human-resources-for-health; referrals; emergency dispatch)? | Is any process on the list out-of-scope or not a priority (e.g. is drug supply a pharmacy function rather than MoH)? | Written endorsement from each programme lead present. | Programme lead says “the real priority is X” → Correction. | Director of Health Services + 8 programme leads | X01 | Pending
B06 | D6 §3.3.2 | The clinical workflow and service-delivery impacts described for each process accurately reflect how health workers currently operate and what they will need in the future. | Has a facility-based clinician actually reviewed the workflow descriptions? If yes, who? | What is the biggest workflow friction likely when moving from paper to digital at a busy HC? | Named clinician reviewer; top-3 friction list. | “No clinician has reviewed this” → Clarification + escalate to rapid clinician review. | Director of Health Services | K09 | Pending
B07 | D6 §3.4 | The e-NHIS enrolment expansion from 15,000–20,000 to 60,000+ beneficiaries via mobile enrolment and eCRVS-NIN integration is feasible. | Does NHIA have call-centre, agent-network and premises capacity for a ~4× enrolment step? | Is the eCRVS API actually ready for real-time eligibility lookup, or is this assumed? | NHIA board endorsement letter; eCRVS API readiness attestation; operational-capacity plan. | “We assume the API will be ready” → Clarification (must be verified). | e-NHIS/NHIA CEO | G02, G06 | Pending

## D Data
Core Validation — Data Architecture (D6 §4)
ID | D6/D7 Ref | Statement | Probe 1 | Probe 2 | Evidence Required | Red-flag Answers | Primary Response Owner | Linked Items | Classification | Verbatim Comment | Proposed Change | Action Owner | Deadline
D01 | D6 §4.1 | The data governance framework (11 domains, Director-level Data Owners, four-tier classification, formal data-sharing agreements) is appropriate for MoH. | For each of the 11 domains, who is the proposed named Data Owner? | Is there a data-sharing MoU template ready, and has DPO reviewed it? | 11-domain Data-Owner list; MoU template; DPO review memo. | “Owners to be named later” → Clarification; cannot Confirm. | DHDD Director + Data Protection Office | G10, L06 | Pending
D02 | D6 §4.2.1 | The MPI strategy (eCRVS NIN as primary identifier, managed through OpenCR with probabilistic matching) is the correct patient-identity approach. | What false-positive / false-negative thresholds are acceptable for probabilistic matching? | For patients without a NIN, what is the enrolment path and who issues a temporary identifier? | Matching threshold policy; unmatched-patient SOP. | “We’ll figure out the thresholds” → Clarification. | DHDD Director + eCRVS/CIVIS lead | G02, G03, A03 | Pending
D03 | D6 §4.2.1 | The data flows between DHIS2, eCRVS, e-NHIS, OpenMRS and A-LIS are accurately and completely described. | Is any major flow missing (e.g. pharmacy, lab-to-clinician)? | Are the described flows validated by the owning system’s technical lead? | Confirmation from each system technical lead; missing-flow list. | System owner doesn’t recognise the flow as described → Correction. | DHDD Director | I02 | Pending
D04 | D6 §4.2.4 | Phased standards adoption (ICD-11 and LOINC first, then SNOMED CT GPS and ATC) is correctly sequenced for MoH’s context and current capacity. | Is local clinical-coding capacity sufficient for ICD-11 in Wave 1, or is training required? | What is the source authority for LOINC code selection (local panel, WHO, reference lab)? | Training plan for coders; LOINC authority source. | “Coders aren’t trained” → Clarification; escalate. | HMIS Coordinator + Lab lead | A07 | Pending
D05 | D6 §4.4 | The role of DHIS2 as national health-analytics platform, with a Wave 3 health-data warehouse, is appropriate. | If an urgent cross-domain analytic need arises in Wave 2, what is the stop-gap? | Who will run the Wave-3 warehouse — DHDD or a separate analytics unit? | Stop-gap plan (e.g. DHIS2 pivot, Superset); governance for the warehouse. | “We’ll deal with Wave-2 analytics when we get there” → Clarification. | DHDD Director | R104 | Pending
D06 | D6 §4.5 | The data-residency requirement — all identifiable health data hosted on sovereign (nationally controlled) infrastructure — is correct in the absence of a national data-protection law. | Does ProgTel/e-Gov DC legally qualify as ‘sovereign’ for the interim? | What happens to PII in the interim period before G-Cloud? | Sovereignty legal opinion; interim PII-handling SOP. | “We’ll clarify sovereignty later” → Objection risk. | PDGA DG + Data Protection Office | L01, L06, T01 | Pending

## A Application
Core Validation — Application Architecture (D6 §5)
ID | D6/D7 Ref | Statement | Probe 1 | Probe 2 | Evidence Required | Red-flag Answers | Primary Response Owner | Linked Items | Classification | Verbatim Comment | Proposed Change | Action Owner | Deadline
A01 | D6 §5.2.1 | DHIS2’s role as the strengthened national HMIS and analytics platform, with Tracker expanded for EIR and case-based IDSR, is correctly described. | Is the DHIS2 instance version current and supported, or does it need an upgrade? | Who will perform Tracker configuration for EIR and IDSR, and under what SLA? | DHIS2 version/support status; Tracker config provider (HISP regional node / MoH). | “The instance is out of support” → Correction. | HMIS Coordinator + HISP regional node | G08, A05, A08 | Pending
A02 | D6 §5.2.2 | OpenHIM as the HIE mediator — the hub through which all systems connect — is the correct platform. | Who will run OpenHIM in production after Wave 1? | Is the required OpenHIM operational skillset inside DHDD, or must it be contracted in? | Operational owner; skills inventory + contract plan. | “We’ll find someone” → Clarification. | DHDD Director | B03, I01 | Pending
A03 | D6 §5.2.3 | OpenCR as the MPI platform, anchored to eCRVS NIN, is the correct choice. | What migration approach is planned for the ~1M eCRVS records becoming the MPI seed? | Does OpenCR deployment require a separate infrastructure spec, or does it co-host with OpenHIM? | MPI seed migration plan; OpenCR infra spec. | “The migration is a detail” → Clarification. | DHDD Director + eCRVS/CIVIS lead | D02, G02 | Pending
A04 | D6 §5.3.1 | OpenMRS as the preferred EHR, deployed first at 15–20 facilities (maternal + HIV/ART) and expanding to 30–40 by 2033, is the right approach. | Have the 15–20 pilot facilities been named, and do the facility managers know? | Is OpenMRS to be deployed vanilla, or are local customisations planned? Who owns them? | Named facility list; customisation plan + owner. | “Facilities to be selected later” → Clarification. | Director of Health Services + MCH / HIV programme leads | B06, K09 | Pending
A05 | D6 §5.3.2 | The phased SPT → DHIS2 Tracker EIR transition over 3–5 years — maintaining SPT until Tracker proves ≥95% equivalence — is correctly planned and appropriately cautious. | How is ≥95% equivalence measured, and over what sample size / duration? | Who owns the measurement, and what is the arbitration path if SPT and Tracker disagree? | Equivalence measurement protocol; arbitrator named. | “We’ll work it out operationally” → Clarification. | EPI programme lead + HMIS coordinator | A01 | Pending
A06 | D6 §5.4.1 | e-NHIS enhancement (mobile enrolment via USSD/app, offline claims following CLAIM-it, eCRVS-NIN integration) — rather than replacement — is the right decision. | Has the NHIA board formally endorsed enhancement over replacement? | Is the CLAIM-it pattern a fit for the current e-NHIS codebase, or does it require forking? | Board endorsement memo; technical fit assessment. | Board hasn’t considered → Clarification + escalate. | NHIA CEO/COO | B07, G06 | Pending
A07 | D6 §5.3.3 | A-LIS strengthening (LOINC coding for 50–80 priority tests, FHIR DiagnosticReport interface, scale to reference and regional labs) is feasible and appropriate. | Is the 50–80 test panel agreed by the National Public Health Lab? | Which labs beyond NPHL will be in scope by Wave 2, and do they have the equipment/skills? | Agreed test panel; lab-expansion list with readiness status. | Panel not agreed → Correction. | National Public Health Lab + Lab lead | D04 | Pending
A08 | D6 §5.5 | Disease-surveillance modernisation (DHIS2 Tracker for case-based IDSR starting with 7 priority notifiable conditions) is correct and builds on existing DHIS2 investment. | Are the 7 priority notifiable conditions confirmed by the IDSR programme and WHO? | What reporting cadence is expected, and is it compatible with facility workloads? | Condition list endorsed; cadence statement. | Condition list disputed → Correction. | IDSR programme lead + WHO | G07, A01 | Pending

## I Integration
Core Validation — Integration Architecture (D6 §6)
ID | D6/D7 Ref | Statement | Probe 1 | Probe 2 | Evidence Required | Red-flag Answers | Primary Response Owner | Linked Items | Classification | Verbatim Comment | Proposed Change | Action Owner | Deadline
I01 | D6 §6.1.2 | The hub-and-spoke integration model (all systems through OpenHIM rather than direct peer connections) is the correct architectural approach. | Are there any existing point-to-point integrations that would be demoted to OpenHIM, and over what timeline? | If OpenHIM is unavailable, is any critical flow blocked, and what is the DR strategy? | Point-to-point decommissioning list; DR plan for OpenHIM. | “DR to be designed later” → Clarification. | DHDD Director | A02, T11 | Pending
I02 | D6 §6.2 | The six priority flows are correctly identified and appropriately sequenced (Flow 1 first; 3–5 in Wave 2; Flow 6 in Wave 3). | Are any flows missing (e.g. pharmacy, referral, mortality)? | Is the Wave-1 Flow 1 realistic given eCRVS, OpenCR, and e-NHIS co-availability? | Missing-flow statement; Wave-1 Flow-1 feasibility note. | “Flow 1 depends on things we don’t control” → Objection. | DHDD Director | A02, A03, G02 | Pending
I03 | D6 §6.1.3 | The three-phase integration maturity progression (batch → API point-to-point → HIE-mediated) is realistic and appropriately paced. | What exit criteria promote a flow from one phase to the next? | Are there any flows that should skip phases, and why? | Phase-exit criteria table; skip-phase exceptions list. | “Phase transitions are judgement calls” → Clarification. | DHDD Director | I02 | Pending
I04 | D6 §6.3 | The three-tier standards approach (FHIR R4 for patient data, ADX for DHIS2 aggregate, FHIR Facade adapters for legacy) is correct. | Which FHIR profiles will be used (IPS, SVCM, MII, custom), and who owns them? | What ADX mapping tables exist, and who maintains them? | Profile owner list; ADX mapping table location. | “Profiles to be defined during build” → Clarification. | DHDD Director + WHO technical lead | G07 | Pending
I05 | D6 §6.2.1 | The statement that SPT-to-DHIS2 is the sole currently operational automated integration accurately reflects the current state. | Are there informal/undocumented automations anywhere (e.g. scheduled scripts, file drops)? | Does the statement include or exclude batch-file loads? | Informal-automation sweep; batch-file inclusion statement. | “There’s one more but it’s half-working” → Correction. | HMIS Coordinator | (D5 premise) | Pending

## T Technology
Core Validation — Technology Architecture (D6 §7)
ID | D6/D7 Ref | Statement | Probe 1 | Probe 2 | Evidence Required | Red-flag Answers | Primary Response Owner | Linked Items | Classification | Verbatim Comment | Proposed Change | Action Owner | Deadline
T01 | D6 §7.1 | The dual-mode hosting strategy (interim ProgTel/e-Gov DC, target G-Cloud via RDIP by 2027) is practical and correctly designed. | Has RDIP given a written commitment to the 2027 G-Cloud delivery date? | What is the migration plan from interim to G-Cloud, and has it been budgeted? | RDIP commitment letter; migration plan + budget line. | “G-Cloud is expected” (no letter) → Objection risk. | PDGA DG + RDIP PM | G01, T05, D06 | Pending
T02 | D6 §7.2.3 | The offline-first mandatory design principle is correct given ~60% national electricity access. | Is every Wave-1 platform choice actually offline-capable, or are some cloud-only? | What endpoint device spec is mandated at facilities (tablet, laptop, solar power, UPS)? | Offline-capability matrix per platform; endpoint spec. | “We’ll require cloud when available” → Correction. | DHDD Director + PDGA | T03 | Pending
T03 | D6 §7.2 | The rural connectivity strategy (EHSSP satellite bridge, RDIP broadband target, offline-first baseline) adequately addresses facility-level gaps. | Who funds the EHSSP bridge (Aug 2025+), and for how long? | Which 30–50 priority facilities are on the short-list, and do they have a working power supply? | Bridge-funding source letter; priority-facility list + power audit. | “The gap will be closed by RDIP” (no letter) → Objection. | PDGA DG + RDIP PM + MoH DHS | G04, K03 | Pending
T04 | D6 §7.4 | Security architecture requirements (TLS 1.2+, AES-256, OAuth 2.0 + mTLS, MFA for admins, RBAC) are appropriate and sufficient. | Is there a national cyber-security baseline MoH must align to beyond these? | Who runs the MFA system — DHDD or PDGA — and what is the break-glass procedure? | National cyber baseline reference; MFA operator + break-glass SOP. | “MFA operations to be decided” → Clarification. | PDGA DG + DHDD Director | (cross-ministry) | Pending
T05 | D6 §7.1.5 | Containerised interim hosting on PDGA/ProgTel is practical for the pre-G-Cloud period. | Does ProgTel/e-Gov DC have Docker/Kubernetes operator skills today? | Is capacity sized for Wave-1 platform set (OpenHIM + OpenCR + DHIS2 + eLMIS)? | Skills audit; capacity-sizing document. | “Capacity to be sized” → Clarification. | PDGA DG | T01 | Pending
T06 | D6 §7.5 | The technology stack (open-source, Docker/Kubernetes, Keycloak) is appropriate and consistent with open-standards and sustainability principles. | Who provides vendor-grade support for each open-source component after Wave 1? | Are any proprietary components still needed, and if so under what licence model? | Support-contract plan per component; proprietary-component list. | “Support to be sourced” → Clarification. | DHDD Director + PDGA DG | K10 | Pending

## R1 Timeline
Core Validation — D7 Roadmap Timeline (D7 §4)
ID | D6/D7 Ref | Statement | Probe 1 | Probe 2 | Evidence Required | Red-flag Answers | Primary Response Owner | Linked Items | Classification | Verbatim Comment | Proposed Change | Action Owner | Deadline
R101 | D7 §4.1 | The three-wave phasing (Wave 1 2025–2026, Wave 2 2027–2029, Wave 3 2030–2033) is logical and correctly sequences governance before technology, infrastructure before applications. | What is the single biggest dependency that could push Wave 1 past 2026? | Is there a risk-adjusted timeline, and has it been sponsored? | Top-risk named; risk-adjusted plan. | “We’ll adjust as we go” → Clarification. | RDIP PM + DHDD Director | K03, K04, K05 | Pending
R102 | D7 §4.2 | Wave 1 priorities are correct (NDHSC/DHDD, OpenHIM + OpenCR, MPI seed, eCRVS → e-NHIS, DHIS2 Tracker pilot, eLMIS rollout, EHSSP transition). | Has every Wave-1 initiative been assigned to a named implementer? | Is Wave-1 Q1 2026 OpenHIM + OpenCR go-live realistic given hosting/skills gaps? | Initiative-to-implementer map; Q1 2026 go-live plan. | “Implementers TBA” → Clarification. | DHDD Director + RDIP PM | B01, A02, A03 | Pending
R103 | D7 §4.3 | Wave 2 priorities are correct (EHR at 15–20, EIR national transition, e-NHIS scaling, G-Cloud migration, full DHDD, 4–5 flows). | Is the EHR pilot funded, or is it pending Wave-2 proposal? | Does G-Cloud migration assume RDIP delivers 2027 on time? | EHR funding status; G-Cloud-dependency flag. | “Pending funding” → Clarification; link to R206. | RDIP PM + DHDD Director | T01, G01, R206 | Pending
R104 | D7 §4.4 | Wave 3 priorities are correct (EHR to 30–40, SPT retirement, all 6 flows at maturity, data warehouse, community surveillance, ≥50% government cost absorption). | Is the ≥50% government absorption a commitment or an aspiration? | What triggers Wave-3 start — a calendar date or a Wave-2 go/no-go? | Commitment classification; Wave-3 start trigger. | “Aspiration” → Objection-risk. | MoH PS + MoF Budget | R204, G09 | Pending
R105 | D7 §4.1.5 | Wave-1 → Wave-2 go/no-go criteria (DHDD ≥6 staff; OpenHIM ≥1 flow; MPI ≥500k records; DHIS2 ≥90% completeness) are appropriate and measurable. | Who measures each criterion, and when in 2026? | What happens if one criterion fails but others pass? | Measurement owner + date; partial-pass decision rule. | “Partial pass is subjective” → Clarification. | DHDD Director + RDIP PM | R102 | Pending
R106 | D7 §4.6 | Critical-path dependencies are correctly identified (governance → data governance → hosting → MPI → HIE → applications). | Is any off-path dependency missing (e.g. endpoint devices, network, power)? | If one step slips, which downstream steps are on hold vs. can proceed in parallel? | Off-path dependency list; slip-propagation analysis. | “We’ll rework if needed” → Clarification. | RDIP PM | T02, T03 | Pending
R107 | D7 §4.2 | The EHSSP W1-11 transition plan (Aug 2025 funding cliff; risk to DHIS2 reporting, SPT, e-NHIS) is an immediate priority and is adequately addressed. | Has the bridge funding actually been committed by a named party (RDIP, government, donor)? | What is the fallback if bridge funding isn’t secured by the cliff date? | Written bridge-funding commitment; fallback plan. | “We’re working on it” (with cliff < 90 days) → Objection. | RDIP PM + MoH PS | G04, K03 | Pending

## R2 Investment
Core Validation — D7 Investment & Sustainability (D7 §5)
ID | D6/D7 Ref | Statement | Probe 1 | Probe 2 | Evidence Required | Red-flag Answers | Primary Response Owner | Linked Items | Classification | Verbatim Comment | Proposed Change | Action Owner | Deadline
R201 | D7 §5.2 | The investment envelope USD 6.2–10.7M (midpoint 8.5M) over 8 years is realistic and proportionate. | Is the range based on bottom-up wave-level costing or top-down benchmark? | Does the midpoint assume all waves at target scope, or some discretion? | Costing methodology statement; midpoint-assumption note. | “Benchmark, refined later” → Clarification. | RDIP PM + DHDD Director | R206, X08 | Pending
R202 | D7 §5.4 | The funding-source mix (RDIP 22–23%, Government 18–19%, Global Fund 14–16%, GAVI 6–8%, others) is realistic and actionable. | Is each donor commitment in writing, or is it mapped based on expected cycles? | What is the tail risk if one major source (RDIP or Global Fund) reduces allocation? | Donor commitment letters; tail-risk analysis. | “Mapped, not committed” → Clarification. | RDIP PM | G09 | Pending
R203 | D7 §5.5 | The Wave-2 funding-gap mitigation (WB/AfDB health-digitisation proposal for USD 0.5–1M) is credible. | Is a concept note already in the pipeline with a named task manager? | What is the decision timeline, and does it leave time before Wave 2 starts? | Concept-note status; WB/AfDB decision-calendar. | “We’ll develop a concept” → Clarification. | MoH PS + RDIP PM | K10 | Pending
R204 | D7 §5.6 | The 6%→75% government absorption trajectory (2025–2033) is realistic. | What is the concrete step to create the government digital-health budget line by 2028? | Which MoF/Budget officer owns the line-creation task? | Budget-line creation plan; named owner at MoF. | “MoF will handle when the time comes” → Objection-risk. | MoH PS + MoF Budget Dept | R205, G09 | Pending
R205 | D7 §5.7 | Government establishes a digital-health budget line by 2028 — acceptable as a commitment from the MoH delegation. | Is this in a signed government commitment letter for RDIP? | What is the escalation path if 2028 slips? | Signed commitment; escalation path. | “Not yet signed” → Clarification; escalate. | MoH PS | R204 | Pending

## R3 Risks
Core Validation — D7 Risk Register (D7 §6)
ID | D6/D7 Ref | Statement | Probe 1 | Probe 2 | Evidence Required | Red-flag Answers | Primary Response Owner | Linked Items | Classification | Verbatim Comment | Proposed Change | Action Owner | Deadline
R301 | D7 §6 | The two Critical risks (EHSSP funding cliff; DHDD recruitment failure) are correctly flagged as Critical. | Are there any currently High risks that, under present evidence, should be upgraded to Critical? | Has anything happened since the draft that downgrades a Critical risk? | Risk-severity re-validation memo. | “The list is a snapshot” → Clarification. | DHDD Director | K01, K03, K04 | Pending
R302 | D7 §6 | The 10 High risks are complete and none are missing (RDIP delay, eCRVS API, NIN production, DPA, EHR adoption, budget-line, ...). | Is clinician burnout in Wave-2 EHR rollout on the High list? | Is vendor lock-in (OpenMRS, OpenHIM) on the list? | Completeness review; missing-risks addition. | Omission acknowledged → Correction. | DHDD Director | K02, K09 | Pending
R303 | D7 §6 | Each risk has a concrete, dated mitigation owner (not just a role). | Is there any risk whose mitigation owner is ‘TBD’ or just a role name? | Is there any risk whose mitigation is financial but has no budget line? | Fully-populated risk register; unfunded-mitigation list. | Any ‘TBD’ owner → Correction. | DHDD Director | K01, K02 | Pending

## R4 Governance
Core Validation — D7 Governance, OKR, OCM, Sustainability (D7 §7)
ID | D6/D7 Ref | Statement | Probe 1 | Probe 2 | Evidence Required | Red-flag Answers | Primary Response Owner | Linked Items | Classification | Verbatim Comment | Proposed Change | Action Owner | Deadline
R401 | D7 §7 | The portfolio-governance structure (NDHSC + DHDD + 3 TWGs + PMO) has clear decision rights and escalation. | Which decisions are at NDHSC, which at TWG, which at DHDD, and where is the escalation path? | Does RDIP PMU sit inside or outside MoH governance? | Decision-rights table; RDIP positioning note. | “Decision rights to be clarified” → Clarification. | MoH PS + DHDD Director + RDIP PM | B01 | Pending
R402 | D7 §7 | The KPI/OKR cascade (portfolio → initiative → operational) is complete. | Is there a KPI for every Wave-1 initiative? | Is the KPI measurable from an existing data source? | Initiative-to-KPI map; data-source readiness. | “KPI measurement TBD” → Clarification. | DHDD Director | B04, R105 | Pending
R403 | D7 §7 | The organisational-change-management plan is adequate for the clinician-facing rollouts (EHR, EIR, IDSR). | Who is the named OCM lead, and what is their experience? | Is there a change-champion network at facility level? | OCM lead; champion network plan. | “OCM is an activity, not a role” → Correction. | Director of Health Services | K09, B06 | Pending
R404 | D7 §7 | The sustainability financial model is credible (steady-state USD 385–515k/yr, 75% government by 2033). | Is the steady-state figure inclusive of support contracts and hosting? | What is the assumed inflation/FX scenario? | Cost breakdown; inflation/FX assumptions. | “Figures are nominal 2025 USD” → Clarification if unstated. | RDIP PM + DHDD Director | R204, R205 | Pending
R405 | D7 §7 | A disciplined review cadence (annual plan refresh, quarterly portfolio review, monthly TWG) is specified. | Are calendar commitments already in PS and DG diaries? | Who chairs each cadence, and what is the quorum? | Calendar commitments; chair + quorum rules. | “Cadence to be set” → Clarification. | MoH PS + DHDD Director | B01 | Pending

## G Commitments
G — External-Party Commitments (RDIP / eCRVS / NHIA / WHO / HISP / MoF / DPO)
ID | Check / Statement | How to Verify (Procedure / Probe) | Evidence Required | Red-flag Pattern | Owner | Status | Notes
G01 | RDIP G-Cloud delivery date formally confirmed (target 2027). | RDIP PM written letter referencing dates. | Commitment letter with board sign-off. | Verbal only → Objection-risk. | RDIP PM | Pending
G02 | eCRVS API readiness for MPI integration confirmed by eCRVS owner. | API spec + readiness date from eCRVS technical owner. | API readiness letter. | “API is planned” → Clarification. | eCRVS/CIVIS lead | Pending
G03 | NIN production resumption timeline confirmed. | Government statement on NIN programme. | Official communiqué. | Verbal only → Clarification. | Ministry of Interior liaison | Pending
G04 | EHSSP bridge funding source confirmed (who pays post-Aug 2025). | Named payer (RDIP, government, donor) in writing. | Funding letter. | No named source → Objection; escalate. | RDIP PM + MoH PS | Pending
G05 | PDGA hosting commitment for interim (ProgTel/e-Gov DC) signed. | PDGA hosting agreement. | Signed hosting agreement with SLA. | “PDGA will host” verbal → Clarification. | PDGA DG | Pending
G06 | NHIA board endorsement of e-NHIS enhancement plan. | NHIA board resolution. | Board minute or resolution letter. | “CEO aware” → Clarification. | NHIA Board / CEO | Pending
G07 | WHO Country Office technical endorsement of surveillance and standards plan. | WHO CR letter. | WHO-CO endorsement letter. | “WHO is supportive” → Clarification. | WHO CR | Pending
G08 | HISP regional node technical endorsement (for DHIS2 Tracker work). | HISP regional node letter. | HISP regional node endorsement. | “HISP will help” verbal → Clarification. | HISP regional node regional lead | Pending
G09 | MoF Budget Dept endorsement of the investment envelope and budget-line path. | MoF letter or minute. | MoF commitment letter. | “MoF will consider” → Objection-risk. | MoF Budget Dept | Pending
G10 | Data Protection Office concurrence on residency and classification in absence of DPA. | DPO concurrence letter. | DPO memo. | “DPO consulted” → Clarification. | Data Protection Office | Pending

## L Legal
L — Legal & Regulatory Prerequisites
ID | Check / Statement | How to Verify (Procedure / Probe) | Evidence Required | Red-flag Pattern | Owner | Status | Notes
L01 | Data Protection Act legislative status and expected enactment date. | Check legislative tracker; named Bill number and stage. | Parliament tracker entry. | “Coming soon” (no Bill) → Clarification. | Data Protection Office | Pending
L02 | Ministerial Order for NDHSC drafted, cabinet-cleared, signable date confirmed. | Drafting status + cabinet schedule. | Draft Order + cabinet agenda. | Not drafted → Correction + escalate. | MoH PS + Cabinet Secretariat | Pending
L03 | Civil Service regulations re DHDD positions (grading, salaries) compatible with 14-position structure. | PSC grading letter. | PSC letter with grades. | “Grades TBD” → Clarification. | PSC + MoH HR | Pending
L04 | Procurement regulations re open-source software deployment compatible with the stack. | Procurement policy review. | Procurement-policy memo. | “Unusual” flags → Clarification. | MoH Procurement + PDGA | Pending
L05 | Cross-border data transfer (WHO / RHO ADX reporting) legality before DPA is in force. | Legal opinion. | Legal opinion memo. | No legal opinion → Objection-risk. | Data Protection Office + WHO | Pending
L06 | Clinical data governance legal basis in absence of DPA (interim instrument). | Ministerial Order or SI. | Interim instrument draft. | No interim instrument → Correction. | MoH PS + DPO | Pending

## X Cross-ref
X — Cross-Reference Integrity (PM runs these between sessions)
ID | Check / Statement | How to Verify (Procedure / Probe) | Evidence Required | Red-flag Pattern | Owner | Status | Notes
X01 | Every D6 §3.3 priority process has a corresponding D7 initiative in at least one wave. | Cross-map 8 processes to W1–W3 initiatives. | Process↔initiative map. | Any orphan process → Correction. | ITU PM | Pending
X02 | Every D6 §5 system disposition maps to a D7 initiative with delivery owner. | Cross-map 8 systems × disposition to initiative cards. | System↔initiative map. | Disposition stated but no initiative → Correction. | ITU PM | Pending
X03 | Every D6 §6 integration flow has a D7 Wave placement and an owning initiative. | Cross-map 6 flows to waves. | Flow↔wave map. | Flow without wave → Correction. | ITU PM | Pending
X04 | D6 §7 technology choices align with D7 Wave-1 milestones (OpenHIM, OpenCR deployed on interim hosting). | Cross-read §7 vs Wave-1 roadmap. | Alignment note. | Misalignment → Correction. | ITU PM | Pending
X05 | D6 capability targets (§3.2 Level 3–4 by 2033) align with D7 investment domain mix (Applications 43%, etc.). | Check: high-maturity capability has proportional investment. | Capability/investment cross-check. | Mismatch → Clarification. | ITU PM | Pending
X06 | D7 go/no-go criteria reference D6 definitions (MPI 500k ↔ §4.2.1; DHIS2 90% ↔ §4.4). | Trace each criterion back to D6. | Trace table. | Un-traceable criterion → Correction. | ITU PM | Pending
X07 | Risk register (D7 §6) references specific D6 architectural dependencies. | Check each risk has D6 §-reference. | Cross-ref list. | Risk without D6 anchor → Correction. | ITU PM | Pending
X08 | Investment figures reconcile: D7 §5 total = sum of wave totals. | Spreadsheet sum check. | Arithmetic check sheet. | Non-reconciling → Correction. | ITU PM | Pending
X09 | Wave 1 USD 1.8–3.0M aligns with sum of Wave-1 initiative-card costs. | Sum initiative-card Wave-1 lines. | Wave-1 cost check. | Out of band → Correction. | ITU PM | Pending
X10 | Terminology consistency: ‘HIE’ = OpenHIM throughout; ‘MPI’ = OpenCR throughout; ‘EHR’ = OpenMRS throughout. | grep across D6 and D7. | Consistency report. | Any alias confusion → Correction. | ITU Analyst | Pending

## K Risks
K — Risk-Register Validation (Day 3 morning)
ID | Check / Statement | How to Verify (Procedure / Probe) | Evidence Required | Red-flag Pattern | Owner | Status | Notes
K01 | Each of the 2 Critical risks has a NAMED individual owner (not a role). | Open risk register; check owner-column content. | Register with named owners. | Role-only owner → Correction. | DHDD Director | Pending
K02 | Each of the 10 High risks has a named mitigation owner with a dated mitigation action. | Register columns Owner + Mitigation-date populated. | Completed register. | Any blank → Correction. | DHDD Director | Pending
K03 | EHSSP funding-cliff mitigation is concrete (named funder, amount, date) — not just ‘W1-11’. | Inspect W1-11 plan. | Concrete bridge plan. | Generic W1-11 reference → Correction. | RDIP PM | Pending
K04 | DHDD recruitment-failure mitigation is credible (named salary bands, secondments, or RDIP supplementation). | Check mitigation statement. | Recruitment mitigation plan. | “Competitive salaries” with no numbers → Clarification. | DHDD Director + PSC | Pending
K05 | RDIP G-Cloud delay risk has a concrete contingency (extended interim hosting, budget top-up). | Inspect contingency. | Contingency plan. | “Extend interim” without budget → Clarification. | RDIP PM | Pending
K06 | eCRVS API unavailability has a Plan B (e.g. flat-file nightly, manual verification). | Check Plan B. | Plan-B doc. | Plan B absent → Correction. | DHDD Director + eCRVS lead | Pending
K07 | NIN production suspension has a probabilistic-matching fallback with acceptable thresholds. | Check fallback. | Matching-threshold SOP. | No fallback thresholds → Clarification. | DHDD Director | Pending
K08 | DPA absence has an interim legal instrument (SI, Ministerial Order) covering health-data exchange. | Check instrument draft. | Interim instrument. | Nothing drafted → Objection-risk. | DPO + MoH PS | Pending
K09 | EHR clinician-adoption risk has a change-management plan with named champions per pilot facility. | Check OCM plan. | OCM plan + champions list. | Generic OCM → Correction. | Director of Health Services | Pending
K10 | Government budget-line commitment has a concrete political mechanism (MoF instruction, budget-circular line). | Inspect mechanism. | Mechanism doc. | Generic aspiration → Objection-risk. | MoH PS + MoF | Pending
K11 | Residual risks after mitigation are truly residual (not just transferred to another line). | Inspect before/after severity. | Residual-risk note. | Transfers disguised as mitigations → Correction. | DHDD Director | Pending
K12 | Risk-review cadence is established (quarterly register refresh; monthly Critical review). | Calendar commitments. | Cadence note. | No cadence → Clarification. | DHDD Director | Pending

## S Coverage
S — Stakeholder Coverage Tracking
ID | Check / Statement | How to Verify (Procedure / Probe) | Evidence Required | Red-flag Pattern | Owner | Status | Notes
S01 | Every core-validation item has a primary response owner who is physically in the room (or on named proxy). | For each item (B/D/A/I/T/R1/R2/R3/R4) verify owner is present. | Attendance register annotated per item. | Owner absent without proxy → item deferred; re-run post-workshop. | ITU Project Manager | Pending
S02 | Every OBJECTION has a documented alternative position from the objector. | Walk objections; missing alternative → chase. | Feedback log alternative column. | Bare objection (no alternative) → escalate. | ITU Analyst | Pending
S03 | Every CORRECTION has proposed alternative text from the corrector. | Walk corrections; missing text → chase. | Feedback log proposed-change column. | Bare correction (no text) → escalate. | ITU Analyst | Pending
S04 | Every CLARIFICATION has a written answer (either in session or in the written-response log). | Walk clarifications; unanswered → assign to Lead Architect 48h. | Clarification answer log. | Unanswered after 48h → escalate. | ITU Project Manager | Pending
S05 | Every ENHANCEMENT has a decision (adopt / defer to backlog / decline with reason). | Walk enhancements; undecided → decide. | Enhancement decision log. | “Will consider” → re-classify as deferred or declined with reason. | DHDD Director | Pending

## PR Process
PR — Process-Integrity Self-Check (close-out)
ID | Check / Statement | How to Verify (Procedure / Probe) | Evidence Required | Red-flag Pattern | Owner | Status | Notes
PR01 | Every Day-1 session ended with all planned classifications logged. | Count scheduled items vs logged classifications. | Day-1 log tally. | Missing classifications → reopen Day 2 morning. | ITU Analyst | Pending
PR02 | Every Day-2 session ended with all planned classifications logged. | As above. | Day-2 log tally. | Missing → reopen Day 3 morning. | ITU Analyst | Pending
PR03 | Every Day-3 session ended with all planned classifications logged. | As above. | Day-3 log tally. | Missing → escalate to written response. | ITU Analyst | Pending
PR04 | Parking-lot has zero open items at end of Day 3 (or each open item has a written-response owner named). | Parking-lot review in S3.5. | Parking-lot close-out sheet. | Open item with no owner → PM assigns. | ITU Project Manager | Pending
PR05 | Decision memo signed by PS, PDGA DG, RDIP PM before adjournment. | Printed memo signed. | Scanned signed memo in PMU file. | Missing signature → workshop not formally closed. | ITU Project Manager | Pending
PR06 | Feedback log e-mailed to all participants within 24h. | Distribution tracker. | Sent-e-mail log. | Missed 24h → remedial send + apology. | ITU Analyst | Pending

## Dashboard
Validation Progress Dashboard
Core validation tabs (classification column J)
Tab | Total | Confirmed | Correction | Clarification | Enhancement | Objection | N/A | Pending | % Closed
B Business | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0%
D Data | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0%
A Application | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0%
I Integration | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
T Technology | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0%
R1 Timeline | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0%
R2 Investment | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
R3 Risks | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0%
R4 Governance | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
CORE TOTAL | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0%
Supplementary tabs (status column G)
Tab | Total | Done | In progress | Pending | Blocked | Failed | N/A | % Done
V0 Pre-workshop | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0%
P Premise | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0%
G Commitments | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0%
L Legal | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0%
X Cross-ref | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0%
K Risks | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0%
S Coverage | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0%
PR Process | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0%
SUPP TOTAL | 72 | 0 | 0 | 72 | 0 | 0 | 0 | 0%
Exit gate for workshop close
Gate 1 | All core items classified (0 Pending) | FAIL
Gate 2 | All supplementary items Done or N/A (no Pending/Blocked/Failed) | FAIL
Gate 3 | Every Objection has disposition (S Coverage S02 Done) | MANUAL VERIFY — see S Coverage tab
Gate 4 | Decision memo signed (PR05 Done) | MANUAL VERIFY — see PR Process tab
Gate 5 | Feedback log distributed (PR06 Done) | MANUAL VERIFY — see PR Process tab