## Slide 1
MODULE 6 · VIDEO 6.3
6.3
The roadmap over time: horizons, waves and tracks
A roadmap sets the years ahead in horizons and the first horizon in waves, each wave with a governance track, a track for each domain and one visible service that shows the result.
standalone video · voice-over on text slides
Notes: Title card — the cold open. The hosts name the module, the video number, the title and the single message on this slide; no scripted narration. Hold until the opener begins; the opener is narrated on the next slide.

## Slide 2
WHERE WE START
A ranked list is not yet a plan.
A plan says what happens in which year, who does it, and what people will see at each step.
That is what the roadmap over time adds to the priorities.
6.3 · The roadmap over time: horizons, waves and tracks
www.itu.int
Notes: VO: A ranked list is not yet a plan. A plan says what happens in which year, who does it, and what people will see at each step. That is what the roadmap over time adds to the priorities.

## Slide 3
Horizons, then waves
H1 Foundation
2027 to 2028.
H2 Scale
2029 to 2030.
H3 Extend
2031 to 2033.
The first horizon in detail
Four waves of six months.
6.3 · The roadmap over time: horizons, waves and tracks
Notes: VO: Set the years ahead in horizons, and write only the first horizon in detail. Progressa's roadmap, built as an example, has three horizons: foundation in 2027 and 2028, scale in 2029 and 2030, and extension from 2031 to 2033. The first horizon runs 24 months, in four waves of six months. PAERA orders a country's start in four phases, from inception to mass-scale transformation. Wave is the roadmap's own word, used inside the first horizon; phase is PAERA's word. UNDP's playbook ends its scoping assessment with the same step: develop the roadmap.
Production cue: Figure F13 (the roadmap over time: horizons and waves) belongs to the written guide and is not on the slide. Text-only.

## Slide 4
Inside each wave
A governance track opens every wave.
A track for each domain with work in the wave.
A beacon
One service people can see.
A wave summary
What must be true before the following wave.
6.3 · The roadmap over time: horizons, waves and tracks
Notes: VO: Each wave has the same parts. It opens with a governance track, because the domain tracks cannot start lawfully or be paid for without it. Then comes a track for each domain that has work in the wave. A beacon project is the roadmap's name for a service people can see, which shows the foundation working. Every wave closes with a summary of what must be true before the following one starts. And each component moves through the five stages of the life cycle that the Universal DPI Safeguards Framework names, from conception and scoping to operations and maintenance.
Production cue: The form of the roadmap is this course's own. Text-only.

## Slide 5
Progressa's first horizon (illustrative)
Wave 1
Decide, and join what already runs.
Wave 2
Build the register.
Wave 3
Beacon B1: register once.
Wave 4
Beacon B2: scholarships paid to the right learner.
6.3 · The roadmap over time: horizons, waves and tracks
Notes: VO: Here are Progressa's four waves. The first decides and joins what already runs: a joint board of the ministry of education and the digital government authority, the drafting of the law, one school identifier, and the ministry's membership of the exchange. The second builds the register and connects it to the identity authority's sign-in; before the third starts, the register holds the records of one district, and at least 95 per cent of them pass the quality gates. The third opens the first beacon: a parent registers a child once. The fourth pays scholarships to verified learners through the Payments block.
Production cue: The worked example E7, built for Progressa; every date illustrative. Text-only.

## Slide 6
The critical path
C-02 → C-06 → C-07 → C-08 → C-14.
The law is drafted in wave 1 and must be in force before the national rollout.
Nothing is scheduled before what it depends on.
6.3 · The roadmap over time: horizons, waves and tracks
Notes: VO: Last, the dependencies. For each component the roadmap lists what it waits for, and the longest chain is the critical path. In Progressa it runs from the law, through the register, the identity connection and the registration service, to the rollout in all 24 districts. The amendment to the education act closes the slowest gap of all, so it is drafted in the first wave, and the rollout waits until it is in force. PAERA describes enterprise architecture as the bridge between the business side and IT. The roadmap puts its target state in order, on one timeline that both sides read.
Production cue: Figure F14 (the matrix of dependencies) belongs to the written guide. Carries the shared-picture argument. Text-only.

## Slide 7
IN ONE SENTENCE
A roadmap sets the years ahead in horizons and the first horizon in waves, each wave with a governance track, a track for each domain and one visible service that shows the result.
Do this on your own sector. Draft the waves of the first horizon, and check their order.
The prompt in the companion material gives you a draft of the waves of the first horizon, each with its governance track, domain tracks, beacon and summary. Before the next video.
6.3 · The roadmap over time: horizons, waves and tracks
www.itu.int
Notes: PRACTICE BOX (on-screen only — never read it, never paraphrase it, never point at it). It replaces the narrated handoff: this video ends on the recap and the Sources slide.
VO: Horizons for the years ahead, waves for the first horizon. Each wave opens with governance, works through each domain and ends with a service people can see.

## Slide 8
Sources
• PAERA v1.0, sections 5.7.1 to 5.7.5 and section 2.3
• UNDP, The DPI Approach: A Playbook, 2023, page 23
• Universal DPI Safeguards Framework, United Nations, 2024, page 6
Find the link in the description.
6.3 · The roadmap over time: horizons, waves and tracks
Notes: Sources slide, held ~5 seconds at the end of the video. Links are compiled into the YouTube description per ITU convention; no URLs read aloud.