## Slide 1
MODULE 1 · VIDEO 1.6
1.6
The lifecycle on one page
Six months from start to a roadmap your minister can take to cabinet. Then ongoing governance. Five phases. Four sign-offs. One continuous practice.
standalone video · voice-over on text slides
Notes: Title card — the cold open. The hosts name the module, the video number, the title and the single message on this slide; no scripted narration. Hold until the opener begins; the opener is narrated on the next slide.

## Slide 2
WHERE WE START
If you take one picture away from this knowledge product, take this one.
The EA lifecycle on a single page.
1.6 · The lifecycle on one page
www.itu.int
Notes: VO: If you take one picture away from this knowledge product, take this one: the EA lifecycle on a single page.
RETRIEVAL MOMENT: before showing the phase table, ask the viewer to guess — from a standing start, how long until a roadmap your minister can take to cabinet? Answer comes on the timeline: six months.

## Slide 3
Five phases. Four sign-offs. Six months to a roadmap.
Discover
What exists today?
3–4 wks
Assess
What is the gap?
6–8 wks
Adapt
What fits our country?
4–6 wks
Plan
How do we get there?
6–8 wks
Execute & Govern
How do we sustain this?
Ongoing
◆ = sign-off by the senior decision-maker. Each phase answers one question and produces one deliverable.
Phases 1–4: about six months, four sign-offs
permanent practice
Screenshot this page for your EA Board room wall.
1.6 · The lifecycle on one page
Notes: VO: Five phases, four sign-offs. The first four take about six months; the fifth is ongoing — your country's permanent way of working.

## Slide 4
Each phase: one question, one deliverable, one sign-off
1
Discover · 3–4 weeks
What exists today? → a Discovery brief, no recommendations yet. Sign-off: the picture is accurate.
2
Assess · 6–8 weeks
What is the gap? → the current state in the four parts of an EA, plus maturity scorecards. Sign-off: the gap analysis reflects ground truth.
3
Adapt · 4–6 weeks
What fits our country? → a localised framework with sourcing decisions. Sign-off: the framework and the build / buy / share approach.
4
Plan · 6–8 weeks
How do we get there? → a roadmap and investment plan, the deliverable your minister takes to cabinet. Sign-off: roadmap approved, budget committed.
5
Execute & Govern · ongoing
How do we sustain this? → a living, governed EA, repository plus practice. Cadence: quarterly Board reviews.
1.6 · The lifecycle on one page
Notes: Rows reveal one at a time, cumulative — the whole lifecycle stays visible while each phase is narrated. In v0.1 of the deck each phase had its own slide; the v0.3 script collapses them onto this one page.
VO: Phase one, Discover. What exists today? Your architects map the current landscape — the strategies in force, the systems, the sector plans, the legal framework — and produce a Discovery brief with no recommendations yet. Sign-off: the picture is accurate enough to build on. Three to four weeks.
VO: Phase two, Assess. What is the gap? Architects compare what they found against PAERA-anchored standards, write the current state in the four parts of an EA, score maturity, and write the gap analysis. Sign-off: it names the right problems in the right order. Six to eight weeks.
VO: Phase three, Adapt. What fits our country? PAERA is a starting point, not a constraint, so architects shape it with sector CIOs and your EA Board — your principles, your sector priorities, and for each building block a build, buy, share or sandbox call. Four to six weeks.
VO: Phase four, Plan. How do we get there? Architects describe the target state and sequence the work into a roadmap with investment estimates. Sign-off: roadmap approved, budget committed. This is the deliverable your minister takes to cabinet. Six to eight weeks.
VO: Phase five, Execute and Govern. How do we sustain this? The approved roadmap becomes a project pipeline, and a small permanent team of two to four senior architects turns the EA from a one-time delivery into a living repository. The Board reviews new projects against the architecture. Quarterly, indefinitely.

## Slide 5
Your minister reviews four times — not every diagram
The picture is accurate
end of Discover
The gap reflects ground truth
end of Assess
Framework + sourcing approach
end of Adapt
Roadmap approved, budget committed
end of Plan
Between sign-offs, the architects work.
The minister’s job in between is to remove obstacles — the political ones, mostly. The technical ones are why the architects were hired.
Discover before you measure. Measure before you adapt. Adapt before you plan. Plan before you execute. Govern always.
1.6 · The lifecycle on one page
Notes: The dependency rule had its own slide in v0.2; the v0.3 script folds it into the sign-off rhythm.
VO: Notice the rhythm. Four sign-offs in six months. Your minister does not review every diagram; they review at four moments, each tied to a defined deliverable. Between sign-offs the architects work, and the minister's job is to remove the political obstacles. And the phases depend on each other, in order: discover before you measure, measure before you adapt, adapt before you plan, plan before you execute, govern always.

## Slide 6
Week 1 to week 26 — then forever
Week 1
Discovery begins
Week 26
Approved roadmap — to cabinet
Ongoing
Governed EA — permanent practice
“Months, not years” is not a slogan. It is the consequence of five phases, each with a clear question, a clear deliverable, and a clear sign-off.
Do this on your own sector. Draft a phase-by-phase RACI for your country's EA programme.
The prompt in the companion material gives you a per-phase RACI matrix plus a list of role gaps to resolve. Before the next video.
1.6 · The lifecycle on one page
Notes: PRACTICE BOX (on-screen only — never read it, never paraphrase it, never point at it). It replaces the narrated handoff: this video ends on the recap and the Sources slide.
VO: Six months from Discovery to an approved roadmap. Then your country in permanent EA-governed mode. That is what 'months not years' actually means. It is not a slogan. It is the consequence of sequencing five phases — each with a clear question, a clear deliverable, a clear sign-off — and committing to the practice that runs after.
(This answers the prediction question posed at the start of the video.)

## Slide 7
Sources
• PAERA v1.0 — §3.1.3 Readiness Assessment
• PAERA v1.0 — §5.4 Organisational Assessment & Roadmap
Find the link in the description.
1.6 · The lifecycle on one page
Notes: Sources slide, held ~5 seconds at the end of the video. Links are compiled into the YouTube description per ITU convention; no URLs read aloud.