## Slide 1
MODULE 5 · VIDEO 5.1
5.1
Plan the build in four phases
Foundation, Pilot, Expansion, Optimisation — four phases with decision gates, an honest calendar, and the four plans beside the schedule that a funder actually reads.
standalone video · voice-over on text slides
Notes: Title card — the cold open. The hosts name the module, the video number, the title and the single message on this slide; no scripted narration. Hold until the opener begins; the opener is narrated on the next slide.

## Slide 2
WHERE WE START
You do not onboard a whole government at once.
Four phases, each delivering something real.
A decision gate before the next phase is funded.
5.1 · Plan the build in four phases
www.itu.int
Notes: VO: You do not onboard a whole government at once. You build the framework in four phases, each delivering something real, each with a decision gate before the next is funded — a pattern drawn from how Estonia and others actually built their buses.
Retrieval prompt — ask before playing on: from the start of the build, how long until the first citizen-visible once-only exchange? Answer on the next slide: about a year.

## Slide 3
Four phases, a gate at each, on an honest calendar
BEFORE MONTH 0
The groundwork: decree, governance, architecture, standards
A year to eighteen months of work
PHASE 1 · MONTHS 0–6
Foundation
Platform and trust anchor live
Two pilot members
PHASE 2 · MONTHS 7–12
Pilot and Validation
First cross-ministry once-only exchanges
Five members
PHASE 3 · MONTHS 13–18
Expansion
First-wave sectors covered
Fifteen members, 20+ services
PHASE 4 · MONTHS 19–24
Optimisation
Performance, the long tail, the next wave
a go / no-go gate — the next phase is funded only if this one delivered
First citizen-visible once-only exchange: about a year in. National coverage: a four-to-six-year programme — say so on day one.
5.1 · Plan the build in four phases
Notes: VO: First, the honest calendar. The four build phases start when the foundation is laid — the decree, the governance, the architecture and the standards portfolio — and that groundwork is itself a year to eighteen months of team effort, longer in calendar time because legislative and budget cycles do not hurry. Then the phases. Phase one, Foundation, months zero to six — the central platform and its trust anchor go live, two pilot members connect, the first services run. Phase two, Pilot and Validation, seven to twelve — the first real cross-ministry once-only exchanges go live, the first five members are on, conformance testing is operating. Phase three, Expansion, thirteen to eighteen — the first-wave sectors are covered: fifteen members, twenty or more services. Phase four, Optimisation, nineteen to twenty-four — performance, the long tail, the next wave of sectors. So the first citizen-visible once-only exchange lands about a year into the build, and the first real milestone — the platform running with a handful of member services — two to three years from the day the programme starts. National coverage is a four-to-six-year programme. Say that to your minister on day one; it is the number that keeps the programme funded when the launch enthusiasm fades. Each phase ends with a decision gate: a go or no-go where the funder and the Steering Committee confirm the phase actually delivered before the next is funded.
Production cue: this slide answers the retrieval prompt set on the opener. Reveal the groundwork first, then the phases left to right.

## Slide 4
Phase one builds the bus once — everything after reuses it
Every later phase and every agency that joins consumes that one investment.
That is what a funder should see in the plan.
A funder paying for a national platform, not a project.
5.1 · Plan the build in four phases
Notes: VO: The phasing protects the re-use logic: phase one builds the shared bus once, and every phase and every agency after it reuses that one investment. A funder who sees that is paying for a national platform, not a project.

## Slide 5
These build phases are not the enterprise-architecture lifecycle
THE FIVE-PHASE LIFECYCLE
Produced your plan.
Designs the target.
THE FOUR BUILD PHASES
Build the bus.
Run inside the lifecycle's final phase.
Same word, two different things — keep them apart in every briefing.
5.1 · Plan the build in four phases
Notes: VO: One caution, because the words collide: these four build phases are not the five-phase enterprise-architecture lifecycle that produced your plan. That lifecycle designs the target; this schedule builds the bus, inside its final phase.

## Slide 6
The plan is five documents, not one schedule
1
The phased schedule
Outcomes, a go / no-go gate and the risks, per phase.
2
The investment plan
Capital and running costs, benchmarked — and the state's line to run what a donor built.
3
The procurement plan
One lot per domain, never one big-bang contract; the platform bought as an accepted result.
4
The workforce plan
The operator from eight to fifteen people towards thirty to eighty; a focal point per member.
5
The risk register and the success metrics
Members, services, transactions, uptime, onboarding time, satisfaction.
A cost frame a funder can check is a cost frame a funder can approve.
5.1 · Plan the build in four phases
Notes: VO: Second, the plan is five documents, not one schedule. The phased schedule — for each phase its outcomes, its gate, its risks. The investment plan — capital and running costs across the years, benchmarked against what comparable platforms cost, and with the state's own budget line for running whatever a donor built, because the commonest failure is a platform funded to launch and not to operate. The procurement plan — one lot per domain, sequenced across the phases, and never a single big-bang contract that hands the architecture to whichever vendor wins; the platform itself is bought as a working, accepted result, with acceptance tests and penalties, against the framework's rules as mandatory requirements. The workforce plan — the operator grows from a first team of eight to fifteen towards thirty to eighty at national scale, and every member needs a named technical focal point. And the risk register with the success metrics — members onboarded, services registered, transactions a quarter, uptime, how long onboarding takes, member satisfaction — reviewed at every gate. A cost frame a funder can check is a cost frame a funder can approve.
Production cue: the pivotal slide of this video. Hold it a beat longer.

## Slide 7
Four phases after the foundation, a gate at each, an honest calendar, and the four plans beside the schedule — a programme a funder can approve.
IN ONE SENTENCE
Do this on your own sector. Draft your implementation plan — the phased schedule and the four plans beside it.
The prompt in the companion material gives you the phased schedule plus the investment, procurement, workforce and risk plans. Before the next video.
5.1 · Plan the build in four phases
www.itu.int
Notes: PRACTICE BOX (on-screen only — never read it, never paraphrase it, never point at it). It replaces the narrated handoff: this video ends on the recap and the Sources slide.
VO: So you plan the build in four phases — Foundation, Pilot, Expansion, Optimisation — each with a gate and a benchmarked cost, on a calendar you have told the truth about, with the investment, procurement, workforce and risk plans beside the schedule. That is what turns an ambition into a fundable programme.

## Slide 8
Sources
• Estonia — X-Road build-out (cost and timeline benchmark)
• ITU DPI Safeguards
• NIIS X-Road implementation guidance (niis.org)
Find the link in the description.
5.1 · Plan the build in four phases
Notes: Sources slide, held ~5 seconds at the end of the video. Links are compiled into the YouTube description per ITU convention; no URLs read aloud.