## Slide 1
1.6 — The lifecycle on one page
KP1 · Government Enterprise Architecture · Module 1 · Video 1.6
Six months from start to a roadmap your minister can take to cabinet. Then ongoing governance. Five phases. Four sign-offs. One continuous practice.
Length: ~5 mins
Target audience: CDO · Director-General · sector minister
THE LIFECYCLE THIS MODULE TEACHES
Discover
Assess
Adapt
Plan
Execute & Govern
4 sign-offs · 6 months to a roadmap · then ongoing
Notes: Title card for standalone video 1.6. Content slides are identical to the corresponding section of the combined deck KP1_M1_Deck_v0.1.pptx; voice-over is in each slide’s notes.

## Slide 2
KP1 · MODULE 1 · VIDEO 1.6
1.6
The lifecycle on one page
Six months from start to a roadmap your minister can take to cabinet. Then ongoing governance. Five phases. Four sign-offs. One continuous practice.
~5 minutes · standalone video · voice-over on text slides
Notes: VO, slide 1: If you take one picture away from this knowledge product, take this one. The EA lifecycle on a single page. The picture that goes on the wall of the EA Board room. The picture your minister puts in every cabinet briefing. The picture your team points at when they explain where the work is.
RETRIEVAL MOMENT: before showing the next slide, ask the viewer to guess — from a standing start, how long until a roadmap your minister can take to cabinet? Answer comes on the timeline: six months.

## Slide 3
Five phases. Four sign-offs. Six months to a roadmap.
Discover
What exists today?
3–4 wks
Assess
What is the gap?
6–8 wks
Adapt
What fits our country?
4–6 wks
Plan
How do we get there?
6–8 wks
Execute & Govern
How do we sustain this?
Ongoing
◆ = sign-off by the senior decision-maker. Each phase answers one question and produces one deliverable.
Phases 1–4: about six months, four sign-offs
permanent practice
The centrepiece of Module 1 — designed to be screenshot and put on the EA Board room wall.
1.6 · The lifecycle on one page
Notes: VO: Five phases. Each one answers a single question. Each produces a single deliverable. Each ends with a sign-off by the senior decision-maker. The first four phases together take about six months. The fifth phase is ongoing — your country's permanent way of working.

## Slide 4
Phase 1 — Discover
QUESTION
What exists today?
DELIVERABLE
Discovery brief — the current picture: strategies in force, systems, sector plans, stakeholders, legal framework. No recommendations yet.
SIGN-OFF
The senior decision-maker confirms the picture is accurate enough to build on.
DURATION
3 to 4 weeks
1.6 · The lifecycle on one page
Notes: VO: Phase one. Discover. The question: what exists today? Your architects map the current digital landscape — the strategies in force, the systems that exist, the sector plans, the stakeholders, the legal framework. The deliverable is a Discovery brief: the picture of where your country is, with no recommendations yet. The sign-off: the senior decision-maker confirms the picture is accurate enough to build on. Three to four weeks.

## Slide 5
Phase 2 — Assess
QUESTION
What is the gap?
DELIVERABLE
Assessment report — current-state picture in the four parts of an EA, maturity scorecards, gap analysis against PAERA-anchored standards.
SIGN-OFF
The gap analysis reflects ground truth — it names the right problems in the right priority.
DURATION
6 to 8 weeks
1.6 · The lifecycle on one page
Notes: VO: Phase two. Assess. The question: what is the gap? Architects compare what they found in Discovery against PAERA-anchored standards. They write the current-state picture in the four parts of an EA. They produce maturity scorecards. They write the gap analysis. The sign-off: the gap analysis reflects ground truth. Six to eight weeks.

## Slide 6
Phase 3 — Adapt
QUESTION
What fits our country?
DELIVERABLE
Localised framework with sourcing decisions — your principles, your sector priorities; per building block: build, buy, share, or sandbox first.
SIGN-OFF
The framework and the build / buy / share approach.
DURATION
4 to 6 weeks
1.6 · The lifecycle on one page
Notes: VO: Phase three. Adapt. The question: what fits our country? PAERA is a starting point, not a constraint. Architects work with sector CIOs and your EA Board to shape the framework to your country. For each building block, the question is: do we build it, do we buy it from the marketplace, do we share another country's, or do we test in a sandbox first? Four to six weeks.

## Slide 7
Phase 4 — Plan
QUESTION
How do we get there?
DELIVERABLE
Roadmap and investment plan — target state, sequenced work, investment estimates. The deliverable your minister can take to cabinet.
SIGN-OFF
Roadmap approved, budget committed — by the senior decision-maker and the EA Board.
DURATION
6 to 8 weeks
1.6 · The lifecycle on one page
Notes: VO: Phase four. Plan. The question: how do we get there? Architects describe the target state and sequence the work into a roadmap with investment estimates. The senior decision-maker and the EA Board approve the roadmap and commit budget. This is the deliverable your minister can take to cabinet. Six to eight weeks.

## Slide 8
Phase 5 — Execute & Govern
QUESTION
How do we sustain this?
DELIVERABLE
A living, governed EA — repository plus practice. The 2–4 permanent architects keep it alive; the EA Board reviews projects against it.
CADENCE
Quarterly Board reviews — indefinitely. New projects reviewed against the architecture; cross-ministry decisions approved; domain boundaries enforced.
DURATION
Ongoing — your country’s permanent way of working
1.6 · The lifecycle on one page
Notes: VO: Phase five. Execute and Govern. The question: how do we sustain this? The approved roadmap becomes a project pipeline. The small permanent EA team — two to four senior architects — turns the EA from a one-time delivery into a living repository. The EA Board reviews new projects against the architecture, approves cross-ministry decisions, enforces boundaries between domains. Quarterly reviews. Indefinitely.

## Slide 9
Your minister reviews four times — not every diagram
The picture is accurate
end of Discover
The gap reflects ground truth
end of Assess
Framework + sourcing approach
end of Adapt
Roadmap approved, budget committed
end of Plan
Between sign-offs, the architects work.
The minister’s job in between is to remove obstacles — the political ones, mostly. The technical ones are why the architects were hired.
1.6 · The lifecycle on one page
Notes: VO: Notice the rhythm. Four sign-offs in six months. Your minister does not review every diagram. They review at four moments, each tied to a defined deliverable. Between sign-offs, the architects work. The minister's job in between is to remove obstacles — the political ones, mostly. The technical ones are why the architects were hired.

## Slide 10
You can skip a phase — and pay for it several times over
Discover before you measure.
Measure before you adapt.
Adapt before you plan.
Plan before you execute.
Govern always.
Skipping usually costs several times what it appeared to save.
1.6 · The lifecycle on one page
Notes: VO: The phases depend on each other, in order. Discover before you measure. Measure before you adapt. Adapt before you plan. Plan before you execute. Govern always. You can skip a phase, but you will pay for it later — usually several times what skipping appeared to save.

## Slide 11
Week 1 to week 26 — then forever
Week 1
Discovery begins
Week 26
Approved roadmap — to cabinet
Ongoing
Governed EA — permanent practice
“Months, not years” is not a slogan. It is the consequence of five phases, each with a clear question, a clear deliverable, and a clear sign-off.
1.6 · The lifecycle on one page
Notes: VO: Six months from Discovery to an approved roadmap. Then your country in permanent EA-governed mode. That is what 'months not years' actually means. It is not a slogan. It is the consequence of sequencing five phases — each with a clear question, a clear deliverable, a clear sign-off — and committing to the practice that runs after.
(This answers the prediction question posed at the start of the video.)

## Slide 12
Sources
• PAERA v1.0 — §3.1.3 Readiness Assessment
• PAERA v1.0 — §5.4 Organisational Assessment & Roadmap
Find the link in the description.
1.6 · The lifecycle on one page
Notes: Sources slide, held ~5 seconds at the end of the video. Links are compiled into the YouTube description per ITU convention; no URLs read aloud.